## Basic Manual Gantt Chart
xsxsx | cdcccx | ccxcxcsc | xcxcxcxc | dvdvvcvbb | ddfsfv
sxsxs | ccxcs | cxcxcsxc | xcxcxcxc | xxcmxcnd | vdvdsvsvdvdv
Campaign Outline & Objectives
| Campaign Area: (TOFU/MOFU/...) | Top of the Funnel |  |  |  | Channels to be used for Campaign Communication:
| Campaign Name: (Awareness/Lead gen...) | Awareness |  |  |  | # of Emails | 3 | 1 | 1 |  | # of SMS messages | 1 | 0.5
| Campaign Objective: (Drive awareness...) | Drive awareness to exising customer, Drive awareness to new prospects |  |  |  | # of Landing Pages | 1 | 2 | 1 |  | Banners | 1 | 1
| Campaign Kick-off Date: (Form filled date - today) | 2018-09-29 |  |  |  | List creation (y/n) | 1 |  |  |  | # of Social posts | 30 | 0.1
| Campaign Start-Date (Tentative): Date mentioned | 2018-10-15 |  |  |  | # of Downloadable assets | 1 | 1 | 3 | 2 | # of Online ads | 0 | 1
| Campaign Start-Date (Actual): | 2018-10-31
| Expected Delay in Campaign Start, if any (in Days) | 16
| Campaign Period (in Months) - 1, 3, 6, 12 | 1
| Campaign Period (in Days) | 30
| Multi-Step Onboarding Campaign Tasks | Task Owner | Start Date | End Date | Duration (in days) | Start Date in Number Form | 43372 |  | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
| Step 1: Campaign Plan Socializing & Approvals |  | 2018-09-29 | 2018-10-08 | 9
| Run the campaign idea & plan with your sales to get buy-in | CMO & CSO | 2018-10-01 | 2018-10-02 | 1
| Run the campaign plan & budgets with your finance tem | CMO & CFO | 2018-10-02 | 2018-10-03 | 1
| Get approvals from the Boss / Manager | CMO & CEO | 2018-10-03 | 2018-10-08 | 3
| Step 2: List Management & Segmentation |  | 2018-10-10 | 2018-10-19 | 9
| Finalize Target Audience criteria | Campaign Manager | 2018-10-10 | 2018-10-11 | 1
| Finalize list quantity & details | Data Expert | 2018-10-11 | 2018-10-12 | 1
| Define segmentation Criteria | Campaign Manager | 2018-10-12 | 2018-10-15 | 1
| Build Target List | Data Expert | 2018-10-15 | 2018-10-19 | 4
| Step 3: Campaign Elements Preparation |  | 2018-10-19 | 2018-10-30 | 11
| Design Campaign Flow | Campaign Manager | 2018-10-19 | 2018-10-22 | 1
| Import Lists in CAMPACT (Campaign Execution Module) | Data Expert | 2018-10-19 | 2018-10-22 | 1
| Define Segments | Data Expert | 2018-10-22 | 2018-10-23 | 1
| Draft Email Content | Content Writers | 2018-10-22 | 2018-10-25 | 3
| Design Emails | Creative Designers | 2018-10-25 | 2018-10-30 | 3
| Draft Landing Pages & Form Content | Content Writers | 2018-10-22 | 2018-10-24 | 2
| Design Landing Pages & Forms | Creative Designers | 2018-10-24 | 2018-10-25 | 1
| Draft & Configure SMS Message | Content Writers | 2018-10-22 | 2018-10-22 | 0.5
| Draft & Schedule Social Media Messages | Content Writers | 2018-10-22 | 2018-10-25 | 3
| Design Banners for Website & Third Party Sites | Creative Designers | 2018-10-22 | 2018-10-23 | 1
| Design & Configure Online Ads | Creative Designers | 2018-10-22 | 2018-10-22 | 0
| Step 4: Building Downloadable Assets |  | 2018-10-23 | 2018-11-06 | 14
| Decide Asset Objective | Campaign Manager | 2018-10-23 | 2018-10-24 | 1
| Outline Asset Framework | Campaign Manager | 2018-10-25 | 2018-10-26 | 1
| Draft Content for Asset | Content Writers | 2018-10-29 | 2018-11-01 | 3
| Design Asset in the output format | Creative Designers | 2018-11-02 | 2018-11-06 | 2
| Step 5: Campaign Launch & Execution |  | 2018-10-31 | 2018-12-12 | 42
| Publish Campaign in CAMPACT and Trigger Start | Campaign Manager | 2018-10-31 | 2018-11-01 | 1
| Send Email Messages | Automated | 2018-11-01 | 2018-11-06 | 3
| Send Social Media Messages | Automated | 2018-11-01 | 2018-12-13 | 30
| Host Banners on Website & Third Party Sites | Ad-tech Automated | 2018-11-01 | 2018-11-02 | 1
| Publish Online Ads | Ad-tech Automated | 2018-11-01 | 2018-11-01 | 0
| Step 6: Campaign Analytics & Reviews |  | 2018-11-09 | 2018-12-21 | 42
| Trigger weekly reports | Automated | 2018-11-09 | 2018-11-15 | 4
| Perform biweekly internal reviews | CMO, Campaign Mgr | 2018-11-21 | 2018-11-23 | 2
| Course Correct - messages, flow, channels (approx 4 times during campaign) | Campaign Manager | 2018-11-09 | 2018-11-15 | 4
| Step 7: Campaign Closure |  | 2018-12-25 | 2018-12-28 | 3
| End Campaign Flow in MAP | Campaign Manager | 2018-12-25 | 2018-12-28 | 3
| Un-publish Channels | Campaign Manager | 2018-12-25 | 2018-12-28 | 3
| Prepare Campaign Closure Report | Campaign Manager | 2018-12-25 | 2018-12-27 | 2
Formulas:
xcxcxcxc = WORKDAY([xcxcxcxc, row above],1)
xcxcxcxc = [dvdvvcvbb, row above]
dvdvvcvbb = MAX([dvdvvcvbb, row below]:E19)
dvdvvcvbb = WORKDAY([xcxcxcxc],[ddfsfv])
Note on I7: Shiv: Yes = 1 No = 0 Affects Cells F17 to 20
Note on C9: Ron Antony: 1 month = 30 days 3 month = 90 days 6 month = 180 d Always on = 365 d
Note on C12: Ron Antony: 1 month = 30 days 3 month = 90 days 6 month = 180 d Always on = 365 d
Note on F14: Ron Antony: Header counts are total number of calendar days. Activity counts are number of work days.